## Jira
Ticket | Title | Release | Description | W-W | W-M | W-W | W-M | Release | W-W | Target
MSGDS-1916 | Ingest M2020 image products and integration with IDS / CS3 | G6.1 Srf Capabilities | Add support for reading M2020 dataproducts and pulling them from CS3 | 14 | 3.5 | 2 | 0.5 | G6.1 Srf Capabilities | 10 | 8
New (replaces MSGDS-1917) | Generate contextual mesh product using ROASTT or Mars Yard dataset | G6.1 Srf Capabilities | Build an example contextual mesh using data captured in the Mars Yard or during the ROASTT | 14 | 3.5 | 8 | 2 | G6.2 Srf Capabilities | 18 | 19.6
MSGDS-2125 | Add support for orbital data products | G6.2 Srf Capabilities | Add support for using orbital (or simulated orbital) data products when generating the contextual mesh | 6 | 1.5 | 3 | 0.8 | G6.3 Srf Capabilities | 7 | 7.8
MSGDS-2123 | Exposure seam correction | G6.2 Srf Capabilities | Corrects for brightness differences between images and removes "patchwork quilt" artifact | 10 | 2.5 | 8 | 2 | G6.4 Srf Capabilities | 9 | 7.8
New (replaces MSGDS-2124) | Increase size of reconstruction area | G6.2 Srf Capabilities | Double the reconstruction volume size from 32 to 64 meters allowing scientists to explore further within a single scene | 8 | 2 | 4 | 1 | G6.5 Srf Capabilities | 10 | 7.8
New (replaces MSGDS-1925) | Sky sphere generation | G6.2 Srf Capabilities | Allows distant terrain and horizon to be efficently rendered as a sky sphere | 6 | 1.5 | 3 | 0.8 | G6.6 Srf Capabilities | 16 | 7.8
MSGDS-1921 | Publish alignment results to PLACES | G6.3 Srf Capabilities | Publish alignment results to places allowing other tools to ingest them | 6 | 1.5 | 2 | 0.5
MSGDS-1907 | Cloud deployment and automatic build process | G6.3 Srf Capabilities | Deploy to the cloud allowing contextual mesh to be automaticlly generated when new data arrives | 12 | 3 | 5 | 1.3
MSGDS-1935 | Overlay support for Reachibility, Roughness, etc. | G6.4 Srf Capabilities | Add support for overlaying different types of products on the contextual mesh | 4 | 1 | 4 | 1
MSGDS-2129 | Multi-viewpoint depth reconstruction | G6.4 Srf Capabilities | Further refine mesh using multi-viewpoint stereo between site drives | 5 | 1.3 | 5 | 1.3
MSGDS-1932 | Validation | G6.5 Srf Capabilities | Validate consistency of mesh against other mission products | 8 | 2 | 2 | 0.5
MSGDS-1929 | Windowed leaf tile generation | G6.5 Srf Capabilities | Enables distributed generation of contextual mesh | 8 | 2 | 8 | 2
MSGDS-2127 | 1st (of 2) Incremental scene updates | G6.6 Srf Capabilities | Allows scenes to be upgraded rather than completly regenerated when new data arrives - increasing performance and reducing generation time / cost | 14 | 3.5 | 8 | 2
MSGDS-2128 | 2nd (of 2) Incremental scene updates | G6.6 Srf Capabilities | Allows scenes to be upgraded rather than completly regenerated when new data arrives - increasing performance and reducing generation time / cost | 6 | 1.5 | 8 | 2
|  |  | TOTAL | 121 | 30.3 | 70 | 17.7